## Task_Table
ID | Name | Duration | Start | Deadline | Resource Names | Notes
| Programming |  |  |  |  | Average $70,000
| prototype code | 12d | 2013-10-10
| build prototype | 3d | 2013-10-22
| test GUI with code | 2d | 2013-10-24
| implement GUI with code feedback | 2d | 2013-10-26
| create animation code prototypes | 10d | 2013-11-05
| test prototypes | 2d | 2013-11-07
| implement prototype feedback | 3d | 2013-11-10
| create level puzzle code prototype | 3d | 2013-11-13
| test code in prototype level | 2d | 2013-11-15
| implement level puzzle feedback | 4d | 2013-11-20
| code first pass of mission codeing | 2d | 2013-11-21
| implement feedback from quest codeing | 2d | 11/23/013
| create traps code, environment tiles randomizer prototypes | 5d | 2013-11-28
| program traps, environment tile prototypes | 5d | 2013-12-05
| test test traps, environment tiles | 2d | 2013-12-07
| implement feedback from traps,environment codeing | 3d | 2013-12-10
| create custom character stats | 4d | 2013-12-14
| test out stat controller | 2d | 2013-12-16
| implement customized character test | 3d | 2013-12-19
| code first pass of multiplayer codeing | 5d | 2013-12-24
| implement any changes from multiplayer code tests | 3d | 2013-12-27
| create monster enemy prototypes round 1 | 4d | 2013-12-31
| test monster enemy codes | 2d | 2014-01-02
| implement feedback from monster enemy codes | 3d | 2014-01-05
| finalize monster round 1 codes | 5d | 2014-01-10
| create monster enemy prototypes round 2 | 1d | 2014-01-11
| test monster enemy codes | 2d | 2014-01-12
| implement feedback from monster enemy codes | 3d | 2014-01-15
| finalize monster round 2 codes | 5d | 2014-01-20
| create healing items prototypes | 5d | 2014-01-25
| test healing items codes | 2d | 2014-01-27
| implement feedback from code test | 2d | 2014-01-28
|  | 5d | 2014-02-02

## Info_Table
Microsoft Project | Template ID: | 4535923402 | (Do Not Edit)
Project is a project management program designed to help you plan, manage, and communicate your projects.
Whether you have a simple list of tasks or want to coordinate activities across multiple projects, Project makes it easy to get started and learn as you go.
This template has been designed to help you to get started in Excel, but when you need more like:
* See your tasks in a Gantt Chart
* Create links between tasks so one task starts after another task finishes
* See how much work each person on the team has assigned to them
You can easily import this information into Project and keep working.