## Task_Table
ID | Name | Duration | Start | Deadline | Resource Names | Notes
| Sound |  |  |  |  | sound mixers start out at about $35,000 a year
| Menu start/load music | 4 days |  |  |  | assistant engineer earns about $18,000 to $28,000 a year
| Beginner level music | 6 days
| Menu sound fx set (5 sounds) | 4 days
| Basic Battle sound fx set 1 (5 sounds) | 6 days
| World interaction sound set 1 (5 sounds) | 4 days
| Character voice sound fx set 1 (5 sounds) | 6 days
| Monster call sound fx set 1 (5 sounds) | 5 days
| Novice level music | 5 days
| Lvl up music | 3 days
| Weather sound fx set (3 sounds) | 3 days
| Song set 1 (3 songs) | 2 weeks
| Song set 2 (3 songs) | 2 weeks
| Song set 3 (3 songs) | 2 weeks
| Basic Battle sound fx set 2 (5 sounds) | 5 days
| Advanced Battle set fx (3 sounds) | 5 days
| Character voice sound fx set 2 (5 sounds) | 5 days
| Monster call sound fx set 2 (5 sounds) | 5 days
| Monster call sound fx set 3 (5 sounds) | 5 days
| World interaction sound set 2 (5 sounds) | 5 days
| World interaction sound set 3 (5 sounds) | 5 days
| Extra sound fx set 1 (10 sounds) | 10 days
| Extra sound fx set 2 (10 sounds) | 10 days
| Clean up sounds | 3 days
| Clean up music | 5 days

## Info_Table
Microsoft Project | Template ID: | 4535923402 | (Do Not Edit)
Project is a project management program designed to help you plan, manage, and communicate your projects.
Whether you have a simple list of tasks or want to coordinate activities across multiple projects, Project makes it easy to get started and learn as you go.
This template has been designed to help you to get started in Excel, but when you need more like:
* See your tasks in a Gantt Chart
* Create links between tasks so one task starts after another task finishes
* See how much work each person on the team has assigned to them
You can easily import this information into Project and keep working.